## Project Plan and Gantt
Project Name | VR Mathematical Concept Visualizaiton
Start Date | 2018-11-16
End Date | 2018-12-07
Tasks | Responsible* | Start | End | Days | Status
Media/PR | Kozak | 2018-11-16 | 2018-12-07 | 21 | Not started
ToolBox Research | Lizka | 2018-11-16 | 2018-11-24 | 8 | Not started
Back End Research | Murdock | 2018-11-16 | 2018-11-24 | 8 | Not started
Purchasing | McWherter | 2018-11-16 | 2018-11-30 | 14 | Not started
Architecture Outline | Lizka, Murdock | 2018-11-24 | 2018-11-30 | 6 | Not started
Equipment Set Up | McWherter | 2018-11-30 | 2018-12-07 | 7 | Not started
Final Fall Meeting |  | 2018-12-07 | 2018-12-07 | 0
*Only senior team members listed

## Milestones
Milestones
Number | Description | Date Intended | Date Completed
1 | Software Architecture Defined | 2018-11-30
2 | Equipment fully set up and operational | 2018-12-07
3 | Pitt News Article Commitment | 2018-12-07