## Project Plan and Gantt
Project Name | VR Mathematical Concept Visualizaiton
Start Date | 2019-01-11
End Date | 2019-03-15
Tasks | Responsible* | Start | End | Days | Status
Media/PR | Kozak | 2019-01-11 | 2019-03-15 | 63 | In Progress
UI Implementation | Murdock | 2019-01-11 | 2019-01-25 | 14 | Not started
Central Bus Implementation | Liszka | 2019-01-11 | 2019-01-25 | 14 | Not started
PC/Vive Set Up | McWherter | 2019-01-11 | 2019-01-18 | 7 | Not started
Secondary VR Set Up | McWherter | 2019-01-18 | 2019-01-25 | 7 | Not started
Object File Generation | McWherter, Liszka | 2019-01-25 | 2019-02-08 | 14 | Not started
File IO | Murdock | 2018-01-25 | 2018-02-08 | 14 | Not started
UI/Central Bus Join | Murdock, Liszka | 2019-02-08 | 2019-02-15 | 7 | Not started
File IO/Central Bus Join | McWherter | 2019-02-08 | 2019-02-15 | 7 | Not started
Object File/Central Bus Join | McWherter, Liszka | 2019-02-15 | 2019-02-22 | 7 | Not started
Package in Application | Murdock, Liszka | 2019-02-22 | 2019-03-01 | 7 | Not started
Testing/Debug | All | 2019-03-01 | 2019-03-15 | 14 | Not started
Release |  | 2019-03-15 | 2019-03-15 | 0
*Only senior team members listed

## Milestones
Milestones
Number | Description | Date Intended | Date Completed
1 | PC/Vive fully set up and operational | 2019-01-18
2 | Test object file generation | 2019-02-08
3 | Pitt News interview completed | 2019-02-15
4 | Code fully implemented | 2019-02-22
5 | Test with HTC Vive Pro | 2019-02-22
6 | Code packaged into Matlab app | 2019-03-01